## Slide 1
INTERNAL ONLY
WORKING DOCUMENT — NOT FOR CLIENT
Work Scope
Project: Tiffany Webb — Landing Page, Kits, Social Media + Add-Ons
Detailed task breakdown + delivery timeline reference

## Slide 2
INTERNAL ONLY
SCOPE — SERVICE 1
Landing Page — Detailed Work Scope
Task | Detail | Output
Copywriting | Hero, about, two-tier topics, signature keynote, testimonials, CTA sections | Final copy doc
Photo/asset placement | Insert provided headshots, event photos, org logos | Populated page
Design & build | Single responsive page, mobile-friendly, on-brand (teal/mint palette) | Live/staged page
Speaker reel embed | Embed provided video or placeholder until reel is ready | Working video block
Booking integration | Contact form + WhatsApp click-to-chat + calendar link | Working booking flow
Domain & hosting check | Confirm domain access, connect hosting, SSL | Live URL
QA pass | Cross-device check, broken link check, spelling/grammar pass | Sign-off ready page
2

## Slide 3
INTERNAL ONLY
SCOPE — SERVICE 2
Media Kit + Capabilities Kit — Detailed Work Scope
Task | Detail | Output
Content mapping | Map her 21 topics into Keynote/Panel vs Workshop/CEU tiers | Topic architecture doc
Media Kit copy (14 pg) | Bio, stats, core message, media coverage, sample Q&A, contact | Full copy draft
Capabilities Kit copy (18 pg) | Positioning, formats, audiences, programs, FAQs, booking process | Full copy draft
Design pass — both kits | Layout, typography, brand colors, photo placement | Designed PDF drafts
Testimonial & logo placement | Insert provided quotes and organization logos | Populated kits
Client review round | Share both kits for feedback, one round of revisions | Revision notes
Final export | Print-ready + web-optimized PDF versions of both kits | Final PDF files
3

## Slide 4
INTERNAL ONLY
SCOPE — SERVICE 3
Social Media Setup — Detailed Work Scope
Task | Detail | Output
Account audit/setup | Instagram, LinkedIn, YouTube, TikTok — create or optimize profiles | 4 optimized profiles
Bio & branding | Consistent handle, bio, profile photo, link-in-bio across all 4 | Unified brand presence
Content pillar system | Define 5 pillars: speaking clips, BTS, tips, quotes, community impact | Content pillar guide
First content batch | 10–14 posts designed from available photos/quotes/footage | Ready-to-post batch
Posting calendar | Week 1 schedule across all platforms, cadence set | Content calendar
Platform-specific formatting | Reels/Shorts for IG & TikTok, articles for LinkedIn, uploads for YouTube | Platform-ready assets
4

## Slide 5
INTERNAL ONLY
SCOPE — ADD-ON 1
WhatsApp AI Assistant — Detailed Work Scope
Task | Detail | Output
WhatsApp Business setup | Number provisioning, verification, business profile | Active WhatsApp Business account
AI flow design | Welcome message, qualification questions, escalation rules | Chatbot flow document
Kit auto-delivery | Instant Media/Capabilities Kit sent on qualified inquiry | Working auto-send trigger
CRM setup | Lead tagging by funnel stage, simple pipeline view | CRM dashboard
Calendar sync | Discovery call booking tied to her calendar | Working booking sync
Reminders & follow-up | Automated call/proposal reminders, post-event testimonial requests | Automated flows live
Testing & handover | End-to-end test of full conversation flow | Signed-off working system
5

## Slide 6
INTERNAL ONLY
SCOPE — ADD-ON 2
PR & Marketing Team — Detailed Work Scope
Task | Detail | Output
Footage intake | Receive raw video from her most recent talk/event | Organized footage folder
Editing pass | Cut 15–20 pieces: reels, shorts, quote cards, clips | Finished content batch
Platform scheduling | Post across Instagram, LinkedIn, YouTube, TikTok on calendar | Scheduled content
Newsletter draft | Monthly newsletter written & designed from same content | Sent newsletter
Community management | Reply to comments & DMs across all platforms | Ongoing engagement
Monthly reporting | Reach, engagement, and inquiry numbers by platform | Monthly report
6

## Slide 7
INTERNAL ONLY
TIMELINE — ORIGINAL 3 SERVICES
4-Day Delivery Sprint
Landing Page + Media/Capabilities Kits + Social Media Setup
DAY 1
Discovery & Draft
Confirm messaging, gather assets (photos, footage, past materials)
Draft kit content outline (both kits)
Landing page copy draft starts
DAY 2
Content Build
Media Kit + Capabilities Kit full copy drafted
Landing page structure & copy locked
Social profiles created/optimized on all 4 platforms
DAY 3
Design & Assembly
Kit design pass — both kits (draft layout)
Landing page built (staging/live draft)
First social content batch designed (10–14 posts)
DAY 4
Review & Launch
Client review round + revisions
Final kit exports (PDF)
Landing page goes live; social goes live with first week of content
7

## Slide 8
INTERNAL ONLY
TIMELINE — WITH ADD-ONS
How Add-Ons Change the Timeline
3 Services Only
Landing page + both kits + social setup
4 days
3 Services + WhatsApp AI
Adds AI flow build, CRM setup, calendar sync, testing
6 days (+2)
3 Services + PR Team
Onboarding runs parallel to Days 1–4; ongoing production after
4 days + ongoing
3 Services + Both Add-Ons
WhatsApp build adds fixed time; PR team runs in parallel & continues
6 days + ongoing
Note: the PR team's ongoing workload scales with how much footage/content she provides each month — the timeline above covers onboarding only, not ongoing monthly production capacity.
8